## Slide 1: Class 2DO Group 152 SPRINT 1
Group members:
LAPR3 2024_2025
Bruno Miguel da Silva (1221514) | Miguel Gonçalves (1221119) | Vitor Carneiro (1240580) | Tomás Teixeira Silva (1240590) | Tiago Silva (1241707) | Jorge Almeida (1220838) | Leonardo Coelho (1171317)
Foto 1 | Foto 2 |  |  |  |  | 

## Slide 2: Sprint planning – Sprint 1
SPRINT BACKLOG | 
Number of stories >14 | 
Number of bugs 0 | 
Number of tasks 0 | 
Number of Management Tasks (Scrum) | 
Number of team members 6 | Planned: 6 Actual: 6
Total planned estimation vs execution | Planned hours: 84 Executed hours: 42
Planned Start Date: 1Week Real Start Date: 5week
Planned Finished Date: 6week Real Finish Date: 6week

## Slide 3: Sprint planning
Assignment US (as stated on project assignment) | Commited? (Yes / no according to team planning) | Todo | Doing | Testing | Done | Blocked
USBD01 | yes |  |  |  | x | 
USBD02 | yes |  |  |  | x | 
USBD03 | yes |  |  |  | x | 
USBD04 | yes |  |  |  | x | 
USBD05 | yes |  |  |  | x | 
USBD06 | yes |  |  |  | x | 
USBD07 | yes |  |  |  | x | 
USBD08 | yes |  |  |  | x | 
USBD09 | yes |  |  |  | x | 
USEI01 | yes |  |  |  | x | 

## Slide 4: Sprint planning
Assignment US (as stated on project assignment) | Commited? (Yes / no according to team planning) | Todo | Doing | Testing | Done | Blocked
USEI02 | yes |  |  |  | x | 
USEI05 | yes |  |  |  | x | 
USLP01 | yes |  |  |  | X | 
USLP02 | yes |  |  |  | x | 

## Slide 5: Work by team member
Chart: Hours or n. tasks
| 1221514 Bruno | 1221119 Miguel | 1240580 Vitor | 1240590 Tomás | 1241707 Tiago | 1220838 Jorge | 1171317 Leonardo
Horas / tarefas | 12 | 11 | 10 | 5 | 2 | 2 | 0

## Slide 6: Work by type
Chart: Epic or Component or UC
| ESINF | BDDAD | LPRA3
Componente | 3 | 9 | 2

## Slide 7: Sprint Burndown Chart
Print do JIRA após fecho da sprint
Chart: 
| dia 1 | dia 5 | dia 10 | dia 15 | dia 20 | dia 25 | dia 30
Sprint 1 | 14 | 14 | 14 | 12 | 12 | 6 | 0

## Slide 8: Sprint Retrospective
Date: 28/10/2024
What went well?
Boa gestão de tempo
Boa distribuição de US
Trabalho em equipa
What went wrong?
Ter entrado no curso no final do sprint 1
Dificuldades para criar grupo
Má gestão de Board(tasks, issues)
Má gestão de Git(branchs, commit “messages”)
A não realização de dailys
What we’ve learned?
Melhorar a gestão de git e board
Diminuir as horas de trabalho instensas
Realizar dailys com todos os membros

## Slide 9: Sprint Retrospective
Date: 28/10/2024
Action items: