## Slide 1: Class 2DO Group 152 SPRINT 3
Group members:
LAPR3 2024_2025
Bruno Miguel (1221514) | Miguel Gonçalves (1221119) | Vitor Carneiro (1240580) | Tomás Teixeira Silva (1240590) | Tiago Silva (1241707) | Jorge Almeida (1220838) | Eduardo Moreira (1190546)

## Slide 2: Sprint planning – Sprint 3
SPRINT BACKLOG | 
Number of stories | 24
Number of bugs | 0
Number of tasks and Sub-Tasks: | 125
Number of Management Tasks (Scrum) | 31
Number of team members 7 | Planned: 7 Actual: 7
Total planned estimation vs execution | Planned hours: 80 Executed hours: 101
Planned Start Date: 25/11/2024 Real Start Date:27/11/2024
Planned Finished Date:05/01/2025 Real Finish Date:05/01/2025

## Slide 3: Sprint planning
Assignment US (as stated on project assignment) | Commited? (Yes / no according to team planning) | Todo | Doing | Testing | Done | Blocked
USBD20 | Yes |  |  |  | X | 
USBD21 | Yes |  |  |  | X | 
USBD22 | Yes |  |  |  | X | 
USBD23 | Yes |  |  |  | X | 
USBD24 | Yes |  |  |  | X | 
USBD25 | Yes |  |  |  | X | 
USBD26 | Yes |  |  |  | X | 
USBD27 | Yes |  |  |  | X | 
USBD28 | Yes |  |  |  | X | 
USBD29 | Yes |  |  |  | X | 
Notes: Não colocar screenshots! Preencher manualmente os valores.

## Slide 4: Sprint planning
Assignment US (as stated on project assignment) | Commited? (Yes / no according to team planning) | Todo | Doing | Testing | Done | Blocked
USAC11 | Yes |  |  |  | X | 
USAC12 | Yes |  |  |  | X | 
USAC13 | Yes |  |  |  | X | 
USAC14 | Yes |  |  |  | X | 
USAC15 | Yes |  |  |  | X | 
USAC16 | No | X |  |  |  | 
USAC17 | Yes |  |  |  | X | 
USAC18 | Yes |  |  |  | X | 
Notes: Não colocar screenshots! Preencher manualmente os valores.

## Slide 5: Sprint planning
Assignment US (as stated on project assignment) | Commited? (Yes / no according to team planning) | Todo | Doing | Testing | Done | Blocked
USEI17 | Yes |  |  |  | X | 
USEI18 | No |  | X |  |  | 
USEI19 | No |  | X |  |  | 
USEI20 | Yes |  |  |  | X | 
USEI22 | No |  | X |  |  | 
USFA03 | Yes |  |  |  | X | 
Notes: Não colocar screenshots! Preencher manualmente os valores.

## Slide 6: Sprint planning
Assignment US (as stated on project assignment) | Commited? (Yes / no according to team planning) | Todo | Doing | Testing | Done | Blocked
USLP05 | Yes |  |  |  | X | 
USLP06 | No | X |  |  |  | 
USLP07 | Yes |  |  |  | X | 
USLP08 | No | X |  |  |  | 
Notes: Não colocar screenshots! Preencher manualmente os valores.

## Slide 7: Work by team member (Sprint 3)
Chart: Hours or n. tasks
| Bruno 1221514 | Miguel 1221119 | Tiago 1241707 | Vitor 1240580 | Tomás 1240590 | Jorge 1220838 | Eduardo 1190546
Horas / tarefas | 22 | 29 | 16 | 23 | 3 | 6 | 2
Notes: Se compilaram o registo de horas colocar as horas de trabalho, caso contrario utilizar o numero de tarefas ou algo que reflita a distribuição de trabalho.

## Slide 8: Work by team member (All Sprints)
Chart: Hours or n. tasks
| Bruno 1221514 | Miguel 1221119 | Tiago 1241707 | Vitor 1240580 | Tomás 1240590 | Jorge 1220838 | Eduardo 1190546
Horas / tarefas | 76.33 | 58.33 | 26 | 46.5 | 18.5 | 13.33 | 4
Notes: Se compilaram o registo de horas colocar as horas de trabalho, caso contrario utilizar o numero de tarefas ou algo que reflita a distribuição de trabalho.

## Slide 9: Work by type
Chart: Epic or Component or UC
| ESINF | ARQC | LAPR | BDDAD
Componente | 2 | 6 | 1 | 4

## Slide 10: Sprint Burndown Chart
Chart: 
| dia 1 | dia 5 | dia 10 | dia 15
Hours | 0 | 8 | 12 | 15
Real | 15 | 14 | 6 | 0
Ideal | 15 | 10 | 5 | 0

## Slide 11: Issues / Assumptions / unanswered questions
Description | Responsible | Date / sprint | Related issue / item in Git
We didn’t find a way to make the Raspberry Pie connect with our personal computers, for wich we had to simulate the machine another way | Members ARQCP | Sprint 3 | USAC15 – Assign na Operatin to a Machine on the Plant Floor
The issue was mainly due to a lack of time, as he was supposed to complete USLP 5, which involved creating the database, but he initially set it up locally instead of using the ISEP server, preventing shared access. | Bruno Silva | Sprint 3 | USPL06 and USPL08

## Slide 12: Daily Meetings (Sprint 3)
Date | Place / duration | Bruno Miguel | Miguel Gonçalves | Vitor | Tiago | Tomas
26-11-2024 | (online) 10 min. | x | x | x | x | x
27-11-2024 | (online) 10 min. | x | x | x |  | x
28-11-2024 | (online) 10 min. | x | x |  | x | 
29-11-2024 | (online) 48 min. | x | x | x |  | x
03-12-2024 | (online) 28 min. | x | x | x | x | 
04-12-2024 | (online) 26 min. | x | x | x |  | 
05-12-2024 | (online) 55 min. | x | x |  | x | 
06-12-2024 | (online) 19 min. | x | x | x |  | 
10-12-2024 | (online) 48 min. | x | x | x | x | 
11-12-2024 | (online) 34 min. | x | x | x |  | 
12-12-2024 | (online) 20 min. | x | x | x |  | 
Notes: Podem criar mais páginas se estas não forem suficientes

## Slide 13: Daily Meetings (Sprint 3)
Date | Place / duration | Bruno Miguel | Miguel Gonçalves | Vitor | Tiago | Team member 5
13-12-2024 | (online) 51 min. | x | x | x |  | 
17-12-2024 | (online) 24 min. | x | x | x | x | 
18-11-2024 | (online) 11 min. | x | x | x |  | 
19-11-2024 | (online) 23 min. | x | x | x | x | 
20-12-2024 | (online) 17 min. | x | x | x |  | 
Notes: Podem criar mais páginas se estas não forem suficientes

## Slide 14: Final Sprint Retrospective (FLAP) Date:
Future considerations:
Improve sprint planning to ensure tasks are completed more efficiently.
Focus on better time management to stay on track and avoid last-minute rushes.
Enhance Git management processes to further streamline collaboration.
Lessons Learned:
Effective communication within the group greatly contributed to progress.
Mutual support and teamwork are key strengths that should be maintained
There's always room for improvement in planning and execution for better outcomes.
Problem Areas:
Sprint planning and time allocation could have been more effective.
Some aspects of Git management, though good, had minor challenges that need refinement.
Accomplishments:
The project ultimately had a positive outcome, reflecting the team's effort and dedication.

## Slide 15: Overall Final Project Mood:
Independently on the team performance, what's the final Team feeling:
Justification: