## BurndownChart
BURNDOWN CHART - GROUP 075
Daily meeting record | Days | Goal | Done | Goal velocity | Remaining | Hours Spent
2025-11-24 | 0 | 0 | 0 | 25 | 25 | 0
2025-11-26 | 1 | 1 | 0 | 24 | 25 | 0
2025-11-28 | 2 | 2 | 0 | 23 | 25 | 0
| 3 | 3 | 0 | 22 | 25 | 0
| 4 | 4 | 0 | 21 | 25 | 0
2025-12-01 | 5 | 5 | 0 | 20 | 25 | 0
2025-12-03 | 6 | 6 | 0 | 19 | 25 | 0
2025-12-05 | 7 | 7 | 0 | 18 | 25 | 0
2025-12-08 | 8 | 8 | 1 | 17 | 24 | 0
| 9 | 9 | 0 | 16 | 24 | 0
| 10 | 10 | 0 | 15 | 24
2025-12-10 | 11 | 11 | 1 | 14 | 23
2025-12-12 | 12 | 12 | 2 | 13 | 21
2025-12-15 | 13 | 13 | 2 | 12 | 19
2025-12-17 | 14 | 14 | 1 | 11 | 18
2025-12-19 | 15 | 15 | 2 | 10 | 16
| 16 | 16 | 0 | 9 | 16
| 17 | 17 | 0 | 8 | 16
2025-12-22 | 18 | 18 | 3 | 7 | 13
2025-12-26 | 19 | 19 | 2 | 6 | 11
2025-12-29 | 20 | 20 | 0 | 5 | 11
| 21 | 21 | 1 | 4 | 10
| 22 | 22 | 1 | 3 | 9
2026-01-01 | 23 | 23 | 3 | 2 | 6
2026-01-02 | 24 | 24 | 3 | 1 | 3
2026-01-03 | 25 | 25 | 3 | 0 | 0
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Insert daily meeting record. Can be Yes/no and the link to Git
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Update according with the days of the sprint
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Update according with the real done items